## Stakeholder Analysis
Stakeholder Analysis
Name | Department / Company | Position | Advisers | Objectives, Requirements, Interests | Influence | Project Contribution | Assumed Resistance
Sir Jojo Castillo | APC ITRO | Project Sponsor |  | Improve client service, Accommodate reequest/inquiries in timely manner, keep the data from the history of engagement of the client/staff and cooperate with the team of developers | High | Provide necessary information for the development op the app (business goals, etc.), supervise the development of the project, provide feedback to the current progress, suggest improvements and additional details to the project, approve the result of the project and the project itself | Refusal to deploy the new System
Sir Alvin C. Limpin | SoCIT Faculty | Project Adviser |  | Provide pivotal advices to the development team and decide the rightful path towards the upbringing of the software application to ensure that it is up to the industry standards. | High | Supervise the development of the project, provide feedback to the current progress, suggest improvements and additional details to the project, answer inquiries | Not willing to provide feedback or communicate with the development team
APC-ITRO | ITRO | Stakeholders |  | Improve client service, Accommodate reequest/inquiries in timely manner, keep the data from the history of engagement of the client/staff | High | Provide input/feedback upon the usability and accessibility of the ITRO Ticketing System as a Staff | Refusal to learn the new system
APC Students, Faculty & Staff | Asia Pacific College | Stakeholders |  | access a more intuitive and user-friendly website for their ITRO-related request and inquiries, easier communication, categorized issues for better filtering and | High | Provide input/feedback upon the usability and accessibility of the ITRO Ticketing System as a Staff | Refusal to use the new system