## WORK PACKAGES COST
RAMs CORNER: ITRO TICKETING SERVICE SYSTEM
Work Packages | Team Member |  |  | Allan Vincent Nefalar |  |  | Bryan Denylle Geneta |  |  | Kieyl Ponce |  |  | Patrick Cortez |  |  | Ruth Morallos |  |  | Vincent Nacor
| Hourly Rate |  |  | 191 |  |  | 125 |  |  | 317 |  |  | 156.25 |  |  | 471.875 |  |  | 282.725
| Depreciation Expenses |  |  | 20.4092 |  |  | 41.6529 |  |  | 27.7941 |  |  | 20.1729 |  |  | 6.4 |  |  | 15.2174
| Estimated Days | Hours Bucket | Hours Left | Hours Worked | Salary | Depr. Expenses | Hours Worked | Salary | Depr. Expenses | Hours Worked | Salary | Depr. Expenses | Hours Worked | Salary | Depr. Expenses | Hours Worked | Salary | Depr. Expenses | Hours Worked | Salary | Depr. Expenses | Total Labor Cost
Initial Planning/Brainstorming | 1 | 8 | 0 | 2 | [5 empty] | 2 |  |  | 1 |  |  | 2 |  |  | 1
Client Selection | 2 | 16 | 6 | 2 | [5 empty] | 2 |  |  | 2 |  |  | 2 |  |  | 2
Project Kick-off meeting | 1 | 8 | 2 | 1 | 191 | 20.4092 | 1 | 125 | 41.6529 | 1 | 317 | 27.7941 | 1 | 156.25 | 20.1729 | 1 | 471.875 | 6.4 | 1 | 282.725 | 15.2174 | 1543.85
Milestone: Project Idea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
First Project Meeting with Members | 1 | 8 | 4 | 1 | 191 | 20.4092 |  | 0 | 0 | 1 | 317 | 27.7941 | 1 | 156.25 | 20.1729 | 1 | 471.875 | 6.4 |  | 0 | 0 | 1136.125
First Project Meeting with Client | 1 | 8 | 4 | 1 | 191 | 20.4092 |  | 0 | 0 | 1 | 317 | 27.7941 | 1 | 156.25 | 20.1729 | 1 | 471.875 | 6.4 |  | 0 | 0 | 1136.125
Project Proposal Initial Creation | 15 | 120 | 105 | 5 | 955 | 102.046 |  | 0 | 0 | 5 | 1585 | 138.9706 | 5 | 781.25 | 100.8646 |  | 0 | 0 |  | 0 | 0 | 3321.25
Second Project Meeting with Members | 1 | 8 | 4 | 1 | 191 | 20.4092 |  | 0 | 0 | 1 | 317 | 27.7941 | 1 | 156.25 | 20.1729 | 1 | 471.875 | 6.4 |  | 0 | 0 | 1136.125
Second Project Meeting with Client | 1 | 8 | 5 | 1 | 191 | 20.4092 |  | 0 | 0 | 1 | 317 | 27.7941 |  | 0 | 0 | 1 | 471.875 | 6.4 |  | 0 | 0 | 979.875
Initial Project Proposal Editing | 2 | 16 | 4 | 4 | 764 | 81.6368 |  | 0 | 0 | 4 | 1268 | 111.1765 | 4 | 625 | 80.6916 |  | 0 | 0 |  | 0 | 0 | 2657
Initial Project Proposal Proofreading | 2 | 16 | 4 | 4 | 764 | 81.6368 |  | 0 | 0 | 4 | 1268 | 111.1765 | 4 | 625 | 80.6916 |  | 0 | 0 |  | 0 | 0 | 2657
Third Meeting with Members | 1 | 8 | 5 | 1 | 191 | 20.4092 |  | 0 | 0 | 1 | 317 | 27.7941 | 1 | 156.25 | 20.1729 |  | 0 | 0 |  | 0 | 0 | 664.25
Third Meeting with Client | 1 | 8 | 4 | 1 | 191 | 20.4092 |  | 0 | 0 | 1 | 317 | 27.7941 | 1 | 156.25 | 20.1729 | 1 | 471.875 | 6.4 |  | 0 | 0 | 1136.125
Project Proposal Revision | 5 | 40 | 16 | 8 | 1528 | 163.2737 |  | 0 | 0 | 8 | 2536 | 222.3529 | 8 | 1250 | 161.3833 |  | 0 | 0 |  | 0 | 0 | 5314
Fourth Meeting with Members | 1 | 8 | 5 | 1 | 191 | 20.4092 |  | 0 | 0 | 1 | 317 | 27.7941 | 1 | 156.25 | 20.1729 |  | 0 | 0 |  | 0 | 0 | 664.25
Fourth Meeting with Client | 1 | 8 | 4 | 1 | 191 | 20.4092 |  | 0 | 0 | 1 | 317 | 27.7941 | 1 | 156.25 | 20.1729 | 1 | 471.875 | 6.4 |  | 0 | 0 | 1136.125
Kick-off meeting for project management planning | 1 | 8 | 5 | 1 | 191 | 20.4092 |  | 0 | 0 | 1 | 317 | 27.7941 | 1 | 156.25 | 20.1729 |  | 0 | 0 |  | 0 | 0 | 664.25
Business Case | 2 | 16 | 0 | 8 | 1528 | 163.2737 |  | 0 | 0 | 4 | 1268 | 111.1765 | 4 | 625 | 80.6916 |  | 0 | 0 |  | 0 | 0 | 3421
Project Charter | 2 | 16 | 0 | 4 | 764 | 81.6368 |  | 0 | 0 | 4 | 1268 | 111.1765 | 8 | 1250 | 161.3833 |  | 0 | 0 |  | 0 | 0 | 3282
Stakeholder Analysis | 2 | 16 | 0 | 4 | 764 | 81.6368 |  | 0 | 0 | 4 | 1268 | 111.1765 | 8 | 1250 | 161.3833 |  | 0 | 0 |  | 0 | 0 | 3282
Stakeholder Management Analysis | 2 | 16 | 0 | 4 | 764 | 81.6368 |  | 0 | 0 | 4 | 1268 | 111.1765 | 8 | 1250 | 161.3833 |  | 0 | 0 |  | 0 | 0 | 3282
Cost Management Analysis | 2 | 16 | 0 | 6 | 1146 | 122.4552 |  | 0 | 0 | 6 | 1902 | 166.7647 | 4 | 625 | 80.6916 |  | 0 | 0 |  | 0 | 0 | 3673
Cost Management Plan | 2 | 16 | 0 | 6 | 1146 | 122.4552 |  | 0 | 0 | 6 | 1902 | 166.7647 | 4 | 625 | 80.6916 |  | 0 | 0 |  | 0 | 0 | 3673
Schedule Management Plan | 2 | 16 | 2 | 6 | 1146 | 122.4552 |  | 0 | 0 | 4 | 1268 | 111.1765 | 4 | 625 | 80.6916 |  | 0 | 0 |  | 0 | 0 | 3039
Scope Management Plan | 2 | 16 | 0 | 6 | 1146 | 122.4552 |  | 0 | 0 | 4 | 1268 | 111.1765 | 6 | 937.5 | 121.0375 |  | 0 | 0 |  | 0 | 0 | 3351.5
Work Breakdown Structure | 2 | 16 | 0 | 4 | 764 | 81.6368 |  | 0 | 0 | 4 | 1268 | 111.1765 | 8 | 1250 | 161.3833 |  | 0 | 0 |  | 0 | 0 | 3282
Work Packages | 2 | 16 | 0 | 6 | 1146 | 122.4552 |  | 0 | 0 | 2 | 634 | 55.5882 | 8 | 1250 | 161.3833 |  | 0 | 0 |  | 0 | 0 | 3030
Human Resource Management Plan | 2 | 16 | 0 | 6 | 1146 | 122.4552 |  | 0 | 0 | 2 | 634 | 55.5882 | 8 | 1250 | 161.3833 |  | 0 | 0 |  | 0 | 0 | 3030
Quality Management Plan | 2 | 16 | 2 | 6 | 1146 | 122.4552 |  | 0 | 0 | 4 | 1268 | 111.1765 | 4 | 625 | 80.6916 |  | 0 | 0 |  | 0 | 0 | 3039
Risk Management Plan | 2 | 16 | 2 | 4 | 764 | 81.6368 |  | 0 | 0 | 4 | 1268 | 111.1765 | 4 | 625 | 80.6916 | 2 | 943.75 | 12.8 |  | 0 | 0 | 3600.75
Communications Management Plan | 2 | 16 | 0 | 6 | 1146 | 122.4552 |  | 0 | 0 | 4 | 1268 | 111.1765 | 6 | 937.5 | 121.0375 |  | 0 | 0 |  | 0 | 0 | 3351.5
Procurement Management Plan | 2 | 16 | 0 | 6 | 1146 | 122.4552 |  | 0 | 0 | 4 | 1268 | 111.1765 | 6 | 937.5 | 121.0375 |  | 0 | 0 |  | 0 | 0 | 3351.5
Implementation Plan | 2 | 16 | 0 | 6 | 1146 | 122.4552 |  | 0 | 0 | 4 | 1268 | 111.1765 | 6 | 937.5 | 121.0375 |  | 0 | 0 |  | 0 | 0 | 3351.5
Change Management Plan | 2 | 16 | 0 | 6 | 1146 | 122.4552 |  | 0 | 0 | 6 | 1902 | 166.7647 | 4 | 625 | 80.6916 |  | 0 | 0 |  | 0 | 0 | 3673
Project Management Plan Editing/Proofreading | 4 | 32 | 16 | 4 | 764 | 81.6368 |  | 0 | 0 | 4 | 1268 | 111.1765 | 8 | 1250 | 161.3833 |  | 0 | 0 |  | 0 | 0 | 3282
Fifth Meeting with Members | 1 | 8 | 5 | 1 | 191 | 20.4092 |  | 0 | 0 | 1 | 317 | 27.7941 | 1 | 156.25 | 20.1729 |  | 0 | 0 |  | 0 | 0 | 664.25
Fifth Meeting with Client | 1 | 8 | 5 | 1 | 191 | 20.4092 |  | 0 | 0 | 1 | 317 | 27.7941 | 1 | 156.25 | 20.1729 |  | 0 | 0 |  | 0 | 0 | 664.25
Project Management Plan Revision | 5 | 40 | 4 | 12 | 2292 | 244.9105 |  | 0 | 0 | 12 | 3804 | 333.5294 | 12 | 1875 | 242.0749 |  | 0 | 0 |  | 0 | 0 | 7971
Sixth Meeting with Members | 1 | 8 | 5 | 1 | 191 | 20.4092 |  | 0 | 0 | 1 | 317 | 27.7941 | 1 | 156.25 | 20.1729 |  | 0 | 0 |  | 0 | 0 | 664.25
Sixth Meeting with Client | 1 | 8 | 5 | 1 | 191 | 20.4092 |  | 0 | 0 | 1 | 317 | 27.7941 | 1 | 156.25 | 20.1729 |  | 0 | 0 |  | 0 | 0 | 664.25
Kick-off meeting for System analysis and Detailed Design | 1 | 8 | 4 | 1 | 191 | 20.4092 |  | 0 | 0 | 1 | 317 | 27.7941 | 1 | 156.25 | 20.1729 | 1 | 471.875 | 6.4 |  | 0 | 0 | 1136.125
Event Table | 5 | 40 | 10 | 10 | 1910 | 204.0921 |  | 0 | 0 | 10 | 3170 | 277.9412 | 10 | 1562.5 | 201.7291 |  | 0 | 0 |  | 0 | 0 | 6642.5
Use Case Diagram | 5 | 40 | 10 | 10 | 1910 | 204.0921 |  | 0 | 0 | 10 | 3170 | 277.9412 | 10 | 1562.5 | 201.7291 |  | 0 | 0 |  | 0 | 0 | 6642.5
Use Case Full Description | 5 | 40 | 10 | 10 | 1910 | 204.0921 |  | 0 | 0 | 10 | 3170 | 277.9412 | 10 | 1562.5 | 201.7291 |  | 0 | 0 |  | 0 | 0 | 6642.5
Context Diagram | 2 | 16 | 4 | 4 | 764 | 81.6368 |  | 0 | 0 | 4 | 1268 | 111.1765 | 4 | 625 | 80.6916 |  | 0 | 0 |  | 0 | 0 | 2657
Data Flow Diagram | 7 | 56 | 6 | 16 | 3056 | 326.5473 |  | 0 | 0 | 10 | 3170 | 277.9412 | 16 | 2500 | 322.7666 | 8 | 3775 | 51.2 |  | 0 | 0 | 12501
Entity Relationship Diagram | 7 | 56 | 20 | 10 | 1910 | 204.0921 |  | 0 | 0 | 6 | 1902 | 166.7647 | 12 | 1875 | 242.0749 | 8 | 3775 | 51.2 |  | 0 | 0 | 9462
Activity Diagram | 4 | 32 | -2 | 12 | 2292 | 244.9105 |  | 0 | 0 | 10 | 3170 | 277.9412 | 12 | 1875 | 242.0749 |  | 0 | 0 |  | 0 | 0 | 7337
Object Diagram | 4 | 32 | 2 | 10 | 1910 | 204.0921 |  | 0 | 0 | 10 | 3170 | 277.9412 | 10 | 1562.5 | 201.7291 |  | 0 | 0 |  | 0 | 0 | 6642.5
Class Diagram | 4 | 32 | 8 | 8 | 1528 | 163.2737 |  | 0 | 0 | 8 | 2536 | 222.3529 | 8 | 1250 | 161.3833 |  | 0 | 0 |  | 0 | 0 | 5314
Sequence Diagram | 3 | 24 | 0 | 8 | 1528 | 163.2737 |  | 0 | 0 | 8 | 2536 | 222.3529 | 8 | 1250 | 161.3833 |  | 0 | 0 |  | 0 | 0 | 5314
State Transition Diagram | 5 | 40 | 16 | 8 | 1528 | 163.2737 |  | 0 | 0 | 8 | 2536 | 222.3529 | 8 | 1250 | 161.3833 |  | 0 | 0 |  | 0 | 0 | 5314
Package diagram | 5 | 40 | 4 | 10 | 1910 | 204.0921 |  | 0 | 0 | 8 | 2536 | 222.3529 | 10 | 1562.5 | 201.7291 | 8 | 3775 | 51.2 |  | 0 | 0 | 9783.5
Component Diagram | 7 | 56 | 18 | 10 | 1910 | 204.0921 |  | 0 | 0 | 10 | 3170 | 277.9412 | 10 | 1562.5 | 201.7291 | 8 | 3775 | 51.2 |  | 0 | 0 | 10417.5
Deployment Diagram | 7 | 56 | 24 | 8 | 1528 | 163.2737 |  | 0 | 0 | 8 | 2536 | 222.3529 | 8 | 1250 | 161.3833 | 8 | 3775 | 51.2 |  | 0 | 0 | 9089
Seventh Meeting with Members | 1 | 8 | 4 | 1 | 191 | 20.4092 |  | 0 | 0 | 1 | 317 | 27.7941 | 1 | 156.25 | 20.1729 | 1 | 471.875 | 6.4 |  | 0 | 0 | 1136.125
System Analysis and Detailed Design Editing/Proofreading | 5 | 40 | 16 | 8 | 1528 | 163.2737 |  | 0 | 0 | 8 | 2536 | 222.3529 | 8 | 1250 | 161.3833 |  | 0 | 0 |  | 0 | 0 | 5314
Seventh Meeting with Client | 1 | 8 | 4 | 1 | 191 | 20.4092 |  | 0 | 0 | 1 | 317 | 27.7941 | 1 | 156.25 | 20.1729 | 1 | 471.875 | 6.4 |  | 0 | 0 | 1136.125
System Analysis and Detailed Design Revision | 10 | 80 | 32 | 15 | 2865 | 306.1381 |  | 0 | 0 | 10 | 3170 | 277.9412 | 15 | 2343.75 | 302.5937 | 8 | 3775 | 51.2 |  | 0 | 0 | 12153.75
Eighth Meeting with Members | 1 | 8 | 4 | 1 | 191 | 20.4092 |  | 0 | 0 | 1 | 317 | 27.7941 | 1 | 156.25 | 20.1729 | 1 | 471.875 | 6.4 |  | 0 | 0 | 1136.125
Eighth Meeting with Client | 1 | 8 | 4 | 1 | 191 | 20.4092 |  | 0 | 0 | 1 | 317 | 27.7941 | 1 | 156.25 | 20.1729 | 1 | 471.875 | 6.4 |  | 0 | 0 | 1136.125
Kick-off meeting for development | 1 | 8 | 3 | 1 | 191 | 20.4092 | 1 | 125 | 41.6529 | 1 | 317 | 27.7941 |  | 0 | 0 | 1 | 471.875 | 6.4 | 1 | 282.725 | 15.2174 | 1387.6
Deliverable: Low fidelity wireframe | 5 | 40 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 20 | 9437.5 | 128 | 20 | 5654.5 | 304.3478 | 15092
Ninth Meeting with member | 1 | 8 | 4 | 1 | 191 | 20.4092 | 1 | 125 | 41.6529 |  | 0 | 0 |  | 0 | 0 | 1 | 471.875 | 6.4 | 1 | 282.725 | 15.2174 | 1070.6
Ninth Meeting with Client | 1 | 8 | 3 | 1 | 191 | 20.4092 | 1 | 125 | 41.6529 | 1 | 317 | 27.7941 |  | 0 | 0 | 1 | 471.875 | 6.4 | 1 | 282.725 | 15.2174 | 1387.6
Deliverable: High Fidelity Wireframe | 10 | 80 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 40 | 18875 | 256 | 40 | 11309 | 608.6957 | 30184
tenth meeting with member | 1 | 8 | 4 | 1 | 191 | 20.4092 | 1 | 125 | 41.6529 |  | 0 | 0 |  | 0 | 0 | 1 | 471.875 | 6.4 | 1 | 282.725 | 15.2174 | 1070.6
tenth meeting with client | 1 | 8 | 5 | 1 | 191 | 20.4092 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 1 | 471.875 | 6.4 | 1 | 282.725 | 15.2174 | 945.6
UI/UX Design/Front End Development | 60 | 480 | 40 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 120 | 56625 | 768 | 320 | 90472 | 4869.5652 | 147097
UI/UX Evaluation | 2 | 16 | 0 | 4 | 764 | 81.6368 |  | 0 | 0 | 4 | 1268 | 111.1765 |  | 0 | 0 | 4 | 1887.5 | 25.6 | 4 | 1130.9 | 60.8696 | 5050.4
11th meeting with members | 1 | 8 | 4 | 1 | 191 | 20.4092 |  | 0 | 0 | 1 | 317 | 27.7941 |  | 0 | 0 | 1 | 471.875 | 6.4 | 1 | 282.725 | 15.2174 | 1262.6
Backend Development | 90 | 720 | 40 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 560 | 264250 | 3584 | 120 | 33927 | 1826.087 | 298177
Verify Use Case Requirements | 10 | 80 | 36 | 12 | 2292 | 244.9105 |  | 0 | 0 | 8 | 2536 | 222.3529 |  | 0 | 0 | 12 | 5662.5 | 76.8 | 12 | 3392.7 | 182.6087 | 13883.2
11th Meeting with the client | 1 | 8 | 0 | 2 | 382 | 40.8184 |  | 0 | 0 | 2 | 634 | 55.5882 |  | 0 | 0 | 2 | 943.75 | 12.8 | 2 | 565.45 | 30.4348 | 2525.2
Unit Testing for Release 1 | 3 | 24 | 0 |  | 0 | 0 | 24 | 3000 | 999.6694 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 3000
Unit Testing for Release 2 | 3 | 24 | 0 |  | 0 | 0 | 24 | 3000 | 999.6694 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 3000
Unit Testing for Release 3 | 2 | 16 | -8 |  | 0 | 0 | 24 | 3000 | 999.6694 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 3000
12th meeting with members | 1 | 8 | 5 |  | 0 | 0 | 1 | 125 | 41.6529 |  | 0 | 0 |  | 0 | 0 | 1 | 471.875 | 6.4 | 1 | 282.725 | 15.2174 | 879.6
Integration Testing | 2 | 16 | 0 |  | 0 | 0 | 8 | 1000 | 333.2231 |  | 0 | 0 |  | 0 | 0 | 4 | 1887.5 | 25.6 | 4 | 1130.9 | 60.8696 | 4018.4
User Acceptance Testing | 2 | 16 | 8 | 2 | 382 | 40.8184 | 4 | 500 | 166.6116 | 2 | 634 | 55.5882 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 1516
Performance Testing | 2 | 16 | 4 |  | 0 | 0 | 4 | 500 | 166.6116 |  | 0 | 0 |  | 0 | 0 | 4 | 1887.5 | 25.6 | 4 | 1130.9 | 60.8696 | 3518.4
Production Readiness Testing | 2 | 16 | 0 | 4 | 764 | 81.6368 | 4 | 500 | 166.6116 | 4 | 1268 | 111.1765 |  | 0 | 0 | 4 | 1887.5 | 25.6 |  | 0 | 0 | 4419.5
Parallel Testing | 2 | 16 | 0 | 2 | 382 | 40.8184 | 6 | 750 | 249.9174 | 2 | 634 | 55.5882 |  | 0 | 0 | 6 | 2831.25 | 38.4 |  | 0 | 0 | 4597.25
13th Meeting with Members | 1 | 8 | 3 | 1 | 191 | 20.4092 | 1 | 125 | 41.6529 | 1 | 317 | 27.7941 |  | 0 | 0 | 1 | 471.875 | 6.4 | 1 | 282.725 | 15.2174 | 1387.6
12th meeting with client | 1 | 8 | 5 | 1 | 191 | 20.4092 |  | 0 | 0 | 1 | 317 | 27.7941 |  | 0 | 0 | 1 | 471.875 | 6.4 |  | 0 | 0 | 979.875
Deployment and Control KickOfff meeting | 1 | 8 | 5 | 1 | 191 | 20.4092 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 1 | 471.875 | 6.4 | 1 | 282.725 | 15.2174 | 945.6
Train General Users | 3 | 24 | 0 | 8 | 1528 | 163.2737 | 8 | 1000 | 333.2231 | 8 | 2536 | 222.3529 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 5064
Set up Kiosk for Localize Deployment | 5 | 40 | 10 | 2 | 382 | 40.8184 | 4 | 500 | 166.6116 |  | 0 | 0 |  | 0 | 0 | 12 | 5662.5 | 76.8 | 12 | 3392.7 | 182.6087 | 9937.2
Deploy the hosted app | 1 | 8 | 0 |  | 0 | 0 | 2 | 250 | 83.3058 | 2 | 634 | 55.5882 |  | 0 | 0 | 2 | 943.75 | 12.8 | 2 | 565.45 | 30.4348 | 2393.2
14th Meeting with Members | 1 | 8 | 3 | 1 | 191 | 20.4092 | 1 | 125 | 41.6529 | 1 | 317 | 27.7941 |  | 0 | 0 | 1 | 471.875 | 6.4 | 1 | 282.725 | 15.2174 | 1387.6
13th meeting with client | 1 | 8 | 5 | 1 | 191 | 20.4092 |  | 0 | 0 | 1 | 317 | 27.7941 |  | 0 | 0 | 1 | 471.875 | 6.4 |  | 0 | 0 | 979.875
Promotion and Advertisement | 5 | 40 | 16 | 8 | 1528 | 163.2737 |  | 0 | 0 | 8 | 2536 | 222.3529 | 8 | 1250 | 161.3833 |  | 0 | 0 |  | 0 | 0 | 5314
Update Documentations | 5 | 40 | 16 | 6 | 1146 | 122.4552 |  | 0 | 0 | 6 | 1902 | 166.7647 | 6 | 937.5 | 121.0375 | 6 | 2831.25 | 38.4 |  | 0 | 0 | 6816.75
Auditing | 5 | 40 | 24 | 8 | 1528 | 163.2737 |  | 0 | 0 | 8 | 2536 | 222.3529 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 4064
Reports and Documentations Handover | 2 | 16 | -2 | 6 | 1146 | 122.4552 |  | 0 | 0 | 6 | 1902 | 166.7647 | 6 | 937.5 | 121.0375 |  | 0 | 0 |  | 0 | 0 | 3985.5
Gain Formal Acceptance | 1 | 8 | 2 | 2 | 382 | 40.8184 |  | 0 | 0 | 2 | 634 | 55.5882 | 2 | 312.5 | 40.3458 |  | 0 | 0 |  | 0 | 0 | 1328.5
Archive Files/Documents | 4 | 32 | 10 | 6 | 1146 | 122.4552 |  | 0 | 0 | 6 | 1902 | 166.7647 | 6 | 937.5 | 121.0375 | 4 | 1887.5 | 25.6 |  | 0 | 0 | 5873
Closeout Meeting with Members | 1 | 8 | 2 | 1 | 191 | 20.4092 | 1 | 125 | 41.6529 | 1 | 317 | 27.7941 | 1 | 156.25 | 20.1729 | 1 | 471.875 | 6.4 | 1 | 282.725 | 15.2174 | 1543.85
TOTAL | 411 | 3288 | 662 | 391 | 74681 | 7980 | 121 | 15125 | 5040 | 340 | 107780 | 9450 | 347 | 54218.75 | 7000 | 875 | 412890.625 | 5600 | 552 | 156064.2 | 8400 | 820759.575

## LAPTOP DEPRECIATION VALUE
Laptop Depreciation Rate(%) | Years
20% | 1.75
DETAILED DEPRECIATION EXPENSES
Team Member | Laptop Price | Years Used | Current Value | Depr. Value | Working Hours | DV per Hour
Allan Vincent Nefalar | 38000 | 2 | 22800 | 7980 | 391 | 20.4092
Bryan Denylle Geneta | 36000 | 3 | 14400 | 5040 | 121 | 41.6529
Kieyl Ponce | 45000 | 2 | 27000 | 9450 | 340 | 27.7941
Patrick Cortez | 50000 | 3 | 20000 | 7000 | 347 | 20.1729
Ruth Morallos | 40000 | 3 | 16000 | 5600 | 875 | 6.4
Vincent Nacor | 40000 | 2 | 24000 | 8400 | 552 | 15.2174

## BUDGET SUMMARY
RAMS Corner: Ticketing Service System
PROJECT DURATION (MONTHS) |  | 21
LABOR COST |  |  |  |  | ROLES | ASSIGNEE | REFERENCES(FOR HOURLY RATES)
ROLE |  | HOURLY RATE | NUMBER OF WORKING HOURS | TOTAL
Project Manager |  | 191 | 391 | 74681 | Project Manager | Allan Vincent Nefalar | https://www.glassdoor.com/Salaries/manila-junior-project-manager-salary-SRCH_IL.0,6_IM995_KO7,29.htm
Product Owner |  | 317 | 340 | 107780 | Product Owner | Kieyl Ponce | https://www.glassdoor.com/Salaries/manila-junior-product-owner-salary-SRCH_IL.0,6_IM995_KO7,27.htm
Scrum Master/Junior Full-Stack Developer |  | 471.875 | 875 | 412890.625 | Scrum Master/Junior Full-Stack Developer | Ruth Morallos | https://www.glassdoor.com/Salaries/manila-scrum-master-developer-salary-SRCH_IL.0,6_IM995_KO7,29.htm
Junior Laravel Developer/UI-UX Designer |  | 282.725 | 552 | 156064.2 | Developer Team Member | Vincent Nacor | https://www.glassdoor.com/Salaries/manila-junior-laravel-developer-salary-SRCH_IL.0,6_IM995_KO7,31.htm
QA Tester |  | 125 | 121 | 15125 | QA Tester | Bryan Geneta | https://www.glassdoor.com/Salaries/manila-junior-qa-tester-salary-SRCH_IL.0,6_IM995_KO7,23.htm
System Trainer |  | 92.5 | 24 | 2220 | System Trainer | STAFF | https://www.glassdoor.com/Salaries/manila-system-trainer-salary-SRCH_IL.0,6_IM995_KO7,21.htm
Documentation Manager |  | 156.25 | 347 | 54218.75 | Documentation Manager | Patrick Cortez | https://www.glassdoor.com/Salaries/manila-documentation-manager-salary-SRCH_IL.0,6_IM995_KO7,28.htm
Cost Estimate for Manpower |  | 822979.575
HARDWARE COST
ITEM |  | TOTAL
Dedicated Server and Computers |  | Legacy
Cost Estimate for Hardware |  | 0
HOSTING AND SECURITY
ITEM NAME | UNIT PRICE | TOTAL UNIT PRICE(12 months) | COUNT | TOTAL
Domain Subscription | 329 | 3948 | 1 | 3948
SSL Subscription
Professional Email
Storage(25GB)
Cost Estimate for Hosting and Security |  | 3948
DEPRECIATION EXPENSES
TEAM MEMBER | CURRENT VALUE (After depreciated in years) |  |  | DEPR. VALUE(20%)
Allan Vincent Nefalar(Laptop) | 22800 |  |  | 7980
Bryan Denylle Geneta(Laptop) | 14400 |  |  | 5040
Kieyl Ponce(Laptop) | 27000 |  |  | 9450
Patrick Cortez(Laptop) | 20000 |  |  | 7000
Ruth Morallos(Laptop) | 16000 |  |  | 5600
Vincent Nacor(Laptop) | 24000 |  |  | 8400
Estimated Depreciation Expenses |  | 43470
INDIRECT COST
UNIT | UNIT PRICE | TOTAL UNIT PRICE | COUNT | TOTAL
Equipments | Covered by APC-ITRO
Administrator
Utilities
ESTIMATED PROJECT COST |  |  | 870397.575
MAINTENANCE (YEARLY) |  |  | Covered by APC-ITRO