## Sheet1
BARANGAY SOUTH SIGNAL VILLAGE - USER ACCEPTANCE TESTING
UAT_TC ID | Business requirement | Acceptance criteria | Test scenario | Test data | Expected outcome | Actual outcome | Status (pass/fail) | Comments/improvements
UAT_TC1.1 | As a Barangay Employee, I want to log in to my account | Should be able to access the employee dashboard | a. Verify if the barangay employee can access Admin Login Page b. Barangay Employee logs in with valid email, password, and recaptcha | Localhost: 127.0.0.1 Hosted: socitcloud.apc.edu.ph/barangay/adminportal E-mal Address: admin@gmail.com Password: Admin1_123 | Should be able to access the employee dashboard
UAT_TC2.1 | As an Admin, I want to create an employee account | Should be able to create an account successfully and receive a success prompt | a. Verify if the Admin can access Manage Employee Account b. Access Manage Employee account from the dropdown c. Creates an account with valid and complete required input | First name: Kieyl Middle name: De Castro No middle name checkbox: unchecked Surname: Ponce Suffix: None Gender: Male Marital Status: Single Nationality: Filipino Birthdate: December 13, 2001 Place of Birth: Taguig, NCR Address-Block No.: Block 7 Address-Street: Quintar Address-Zone/Purok: Zone 1 Employee ID: 1234567 Email Address: kieyldecastroponce.13@gmail.com Mobile number: 9123456789 Password: Kponce013! Confirm Password: Kponce013! Role: Barangay Request Manager Upload Photo: peakpx(2).jpg | Should be able to create a new account for Kieyl, see the account from the list successfully, and receive a success prompt
UAT_TC2.2 | As an Admin, I want to be able to deactivate an employee account | Should be able to deactivate the account | a. Click the Deactivate button from the list of Barangay Employee Account b. Deactivate an account by inputting correct password on the deactivation prompt | Password: Admin1_123 | Should be able to deactivate the account and remove the account from the active list
UAT_TC2.3 | As an Admin, I want to be able to reactivate an employee account | Should be able to succesfully recover the account | a. Access the Deactivated Employee Account b. Reactivates an account by selecting from the list and inputting correct passowrd on the reactivation prompt | Password: Admin1_123 | Should be able to succesfully recover the account and see the account on the active list
UAT_TC2.4 | As an Admin I want to be able to edit an employee account | Should be succesful in updating the account information with success prompt | a. Access the Active Employee List b. View an account from the slist c. Clicks "Edit" buttopn from the Employee detail page d. Updates an account with valid and complete required input | First name: Kieyl Middle name: De Castro No middle name checkbox: unchecked Surname: Ponce Suffix: None Gender: Male Marital Status: Married Nationality: Filipino Birthdate: December 13, 2001 Place of Birth: Taguig, NCR Address-Block No.: Block 9 Address-Street: Quintar Address-Zone/Purok: Zone 12 Employee ID: 1234567 Email Address: kieyldecastroponce.13@gmail.com Mobile number: 9123456789 Password: Kponce013! Confirm Password: Kponce013! Role: Barangay Request Manager Upload Photo: peakpx(2).jpg | Should be succesful in updating Kieyl's account information with success prompt
UAT_TC2.5 | As a Barangay Employee, I want to edit my account | Account details should be updated with success message | a. Clicks the account setting from the profile picture b. Clicks the "Change Password" button and fill up the Old, New and Confirm Password input c. Clicks "Change Email Button" and fill out the form with new email d. Clicks "Change Mobiole Number" and fill out the form with new number e. Updates the account with correct and valid input | Old Password: Admin1_123 New Password: Admin_11 Confirm New Password: Admin_11 New Email: admin11@gmail.com Mobile No.: +63987654321 | Password should be updated with success message Email should be updated with success message Mobile Number should be updated with success message
UAT_TC3.1 | As an Admin, I want to be able to deactivate a resident account | Selected account should be deactivated with success message | a. Access Manage Resident account b. Access the List of Resident Account c. Select an account from the list and deactivate the account by inputting correct password in the deactivation prompt | Password: Admin1_123 | Selected account should be deactivated with success message and removed from the active resident list
UAT_TC3.2 | As an Admin, I want to be able to reactivate resident account | Should be able to succesfully reactivate the account with success message | a. Access Deactivated Resident account b. Select an account from the list and reactivate the account by inputting correct password in the reactivation prompt | Password: Admin1_123 | Selected account should be reactivated with success message and added back to the active resident list
UAT_TC4.1 | As an Admin, I want to edit the homepage banner | The banner should be updated in the home page | a. Click Manage Website b. Click Edit Banner Button c. Click Update Banner button and choose between Banners 1-4 d. Add Image in the choose image input e. Updates the banner with new/old image | Image Name: Banner1.png | Banner #1 should be updated in the home page
UAT_TC4.2 | As an Admin, I want to edit the demography in the home page | The demography should be updated with the new information in the home page and success message | a. Click Manage Website b. Click Edit Demography Button c. Update the demography with new/old information | Total Land Area: 802100 Population: 42997 Registered Voters: 22959 Household: 8507 No. of Puroks: 57 No. of Streets: 64 No. of Polling Preints: 104 | Demography should be updated with the new information in the home page and success message
UAT_TC4.3 | As an Admin, I want to edit the contacts in the home page | The contacts should be updated with the new information in the home page and success message | a. Click Manage Website b. Click Edit Contacts Button c. Update the contacts with new/old information | Telephone: 88660789 Smart: 09491551111 Sun: 09236152389 Globe: 09956531922 Fire Station: 88370740 Taguig Rescue: 86407006 Taguig Police: 86423582 Police Station 6: 09171843906 | Contacts should be updated with the new information in the home page and success message
UAT_TC4.4 | As an Admin, I want to edit the Barangay Officials in the home page | The barangay officials should be updated with the new information in the home page and success message | a. Click Manage Website b. Click Edit Barangay Officials Button c. Update the List of Barangay Officials with new/old, valid, and complete information | Barangay Captain Full Name: Hon. Michelle Ann M. Odevilas Upload Image: capt.jpg Comitee on ways and means: Full name: Hon Kieyl V. Ponce Upload Image: wm.jpg | Barangay officials should be updated with the new information in the home page and success message
UAT_TC5.1 | As a Barangay Secretary, I want to manage the services | Should be able to choose between "Active/Inactive" in the dropdown of Action Column | a. Clicks "Manage Service" b. From the list, set a service as "Active/Inactive" c. Updates the service with new Actions | No Input Required | Should be able to set a service between "Active/Inactive" in the dropdown of Action Column
UAT_TC5.2 | As a Barangay Secretary, I want to view the document request | Should be able to view the information submitted by the requestor | a. Access the View Document Request page b. View a detailed request from the list c. Optional: Download the list as PDF/Excel | No Input Required | Should be able to view the details of the information submitted by the requestor
UAT_TC5.3 | As a Barangay Secretary, I want to process the document request | Should be able to reassign a request to the barangay employee who are logged in | a. Access Process Document Request b. Click "Process" button from the list c. Click "Reassign" button d. Confirm reassigning the request | No Input Required | Should be able to reassign a request to the barangay secretary
UAT_TC5.4 | As a Barangay Secretary, I want to approve a document request | Should proceed to accept document request and be prompted with a success message | a. Click "Process" from the detailed view of the Document Request with a "Paid" status b. Select "Accept" c. Input a avalid date and note in the Acceptance Prompt d. Confirm the Request by inputting correct password | Date: 09/24/2023 - 09/25/2023 Note: "This is a valid note" Password: Secretary_123 | Should proceed to accept document request and be prompted with a success message and change the status to "Accepted"
UAT_TC5.5 | As a Barangay Secretary, I want to deny a document request | Should proceed to deny document request and be prompted with a success message | a. Click "Process" from the detailed view of the Document Request with any status b. Select "Deny" c. Input a valid note in the Deny Prompt d. Deny the request by inputting correct password | Note: "This is a valid note" Password: Secretary_123 | Should proceed to deny document request, be prompted with a success message, and set the status to "Denied"
UAT_TC6.1 | As a Barangay Secretary, I want to view a concern | Should be redirected to a page with the submitted concern | a. Access the View Concern b. Select a concern from the list and view the details | No Input Required | Should be redirected to a page with the detailed view of submitted concern
UAT_TC6.2 | As a Barangay Secretary, I want to process a concern | Should be able to reassign a concern to the barangay employee who are logged in | a. Access Process Concern b. Selects a concern from the list and click "Process" c. Click "Reassign" button d. Confirm the reassigning of the concer | No Input Required | Should be able to reassign a concern to the barangay secretary
UAT_TC6.3 | As a Barangay Secretary, I want to update a concern | Should proceed to update concern and be prompted with a success message | a. Click "Update" from the Detailed view of the concern b. Input valid and complete Title and Detail c. Confirm the Update by inputting correct password | Title: "This is a valid note" Detail: "This is a valid detail" Password: Secretary_123 | Should proceed to update concern, be prompted with a success message and set the status as "Updated"
UAT_TC6.4 | As a Barangay Secretary, I want to deny a concern | Should proceed to deny request and be prompted with a success message | a. Click "Deny" from the Detailed view of the concern b. Input valid and complete Detail c. Confirm the Update by inputting correct password | Detail: "This is a valid detail" Password: Secretary_123 | Should proceed to deny request, be prompted with a success message, and change the concern status to "Denied"
UAT_TC6.5 | As a Barangay Secretary, I want to close a concern | Should proceed to close the concern and be prompted with a success message | a. Click "Close" from the Detailed view of the concern b. Input valid and complete Detail c. Confirm the Update by inputting correct password | Detail: "This is a valid detail" Password: Secretary_123 | Should proceed to close the concern, be prompted with a success message and change the status to "Concern"
UAT_TC7.1 | As a Barangay Captain, I want to view the barangay data report | Should expand to show the statistics regarding the number of requests/concerns received daily, weekly, monthly and/or yearly as well as the Resident and Barangay Employee Statistic Reports | a. Click the dropdown of Reports from the Dashboard b. Click Services from the dropdown c. Click Show Request Statistics from the dropdown d. Click Show Concern Statistics from the dropdown e. Click Resident Statistics from the dropdown f. Click Employee Statistics from the dropdown e. Click Barangay Employee List from the dashboard | No Input Required | Should expand to show the statistics regarding the number of requests/concerns received daily, weekly, monthly and/or yearly as well as the Resident and Barangay Employee Statistic Reports
UAT_TC8.1 | As a Barangay Treasurer, I want to view a list of payment | Should be redirected to the Payment Details page | a. Access The List of Payment b. Select an item from the list and view the detailed receipt | No Input Required | Should be able to see the Payment Details page
UAT_TC8.2 | As a Barangay Treasurer, I want to process an onsite payment | Should be able to confirm the payment and change the Requested Document Status to "Paid" | a. Access Manage Payment b. Access Process Onsite Payment from the dropdown c. Select an Item from the list and click "Process" button d. View the Detailed Payment and click "Proceed" button e. Input valid and complete OR and CTC Number d. Click "Confirm" button | OR No.: 1234567890 CTC No.: 12345 | Should be able to confirm the payment and change the Requested Document Status to "Paid"
UAT_TC8.3 | As a Barangay Treasurer, I want to process an online payment | Should be able to confirm the payment and change the Requested Document Status to "Paid" | a. Access Manage Payment b. Access Process Online Payment from the dropdown c. Select an Item from the list and click "Process" button d. View the Detailed Payment and click "Proceed" button e. Input valid and complete Reference, OR, and CTC Number d. Click "Confirm" button | Ref No: 123455 OR No.: 1234567890 CTC No.: 12345 | Should be able to confirm the payment and change the Requested Document Status to "Paid"