## M1-BarangayEmployeeAuthenticate
TEST CASE PLANNING AND EXECUTION
| TEST TITLE | PRIORITY | TEST CASE ID | TEST NUMBER |  | TEST DATE |  |  | PRIORITY KEY
| Barangay Employee Authentication | HIGH | TC_01-TC_04 | 4 |  | 2023-09-28 |  |  | LOW
| TEST DESCRIPTION |  | TEST DESIGNED BY | TEST EXECUTED BY |  | EXECUTION DATE |  |  | MEDIUM
| Test on authenticating employees |  | Ruth R. Morallos | Ruth R. Morallos |  | 2023-09-28 |  |  | HIGH
| TEST DESCRIPTION |  | TEST DEPENDENCIES | TEST CONDITIONS
| Test on authenticating employees |  | The database for the User should be working. | Barangay Employees must be able to access the website.
Test Case ID | STEPS | TEST DATA | PRE-REQUISITE | EXPECTED RESULTS | ACTUAL RESULTS[SPRINT 1] | PASS / FAIL | ADDITIONAL NOTES | TEST DATE
UC1.1 LOG-IN BARANGAY EMPLOYEE ACCOUNT
TC_01 | Verify if the barangay employee can access Admin Login Page | Localhost: 127.0.0.1 Hosted: socitcloud.apc.edu.ph/barangay/adminportal |  | Should be able to access admin portal website | Had an access to the admin portal website | PASS |  | 2023-09-18
TC_02 | Barangay Employee logs in with valid email, password, and recaptcha | E-mal Address: admin@gmail.com Password: Admin1_123 | M1-UC1.1-TC_01 | Should be able to access the employee dashboard | Had an access to the employee dashboard | PASS |  | 2023-09-18
TC_03 | Barangay Employee logs in with invalid email or password or recaptcha | E-mal Address: resident@gmail.com Password: Admin1_123 or E-mal Address: admin@gmail.com Password: Admin1 | M1-UC1.1-TC_01 | Should receive an invalid input error message and not be able to access the employee dashboard | Invalid email/password/captcha error message, goes back to log in page | PASS |  | 2023-09-18
TC_04 | Barangay Employee logs in with non-existing email or password | E-mal Address: administrator@gmail.com Password: Administrator12345 | M1-UC1.1-TC_01 | Should receive an invalid input error message and not be able to access the employee dashboard | Invalid email/password/captcha error message, goes back to log in page | PASS |  | 2023-09-18

## M2-Manage Employee Account
TEST CASE PLANNING AND EXECUTION
| TEST TITLE | PRIORITY | TEST CASE ID | TEST NUMBER | TEST DATE |  |  |  | PRIORITY KEY
| Manage Employee Account | HIGH | TC_05 - TC_46 | 6 | 2023-09-28 |  |  |  | LOW
| TEST DESCRIPTION |  | TEST DESIGNED BY | TEST EXECUTED BY | EXECUTION DATE |  |  |  | MEDIUM
| Test on Managing Employee Accounts |  | Ruth R. Morallos | Ruth R. Morallos | 2023-09-28 |  |  |  | HIGH
| TEST DESCRIPTION |  | TEST DEPENDENCIES | TEST CONDITIONS
| Test on Managing Employee Accounts |  | The database for the User should be working. | Administrator, Barangay Captain, Barangay Secretary, Request Manager, and/or Concern Manager should be logged in but in the admin portal.
Test Case ID | STEPS | TEST DATA | PRE-REQUISITE | EXPECTED RESULTS | ACTUAL RESULTS[SPRINT 1] | PASS / FAIL | ADDITIONAL NOTES | TEST DATE
UC2.1 Admin-Create Employee Account
TC_05 | Verify if the Admin can access Manage Employee Account | No input required | M1-UC1.1-TC_02 | A dropdown should be shown with list of employee management functions | A dropdown showed the list of employee management functions | PASS |  | 2023-09-21
TC_06 | Verify if the Admin can access Add Employee Account from the dropdown | No input required | M2-UC2.1-TC_05 | Should be redirected to the Add Employee Account Form | Redirected to the Add Employee Account Form | PASS | function is working except for the routing in hosted site | 2023-09-21
TC_07 | Admin creates an account with valid and complete required input | First name: Kieyl Middle name: De Castro No middle name checkbox: unchecked Surname: Ponce Suffix: None Gender: Male Marital Status: Single Nationality: Filipino Birthdate: December 13, 2001 Place of Birth: Taguig, NCR Address-Block No.: Block 7 Address-Street: Quintar Address-Zone/Purok: Zone 1 Employee ID: 1234567 Email Address: kieyldecastroponce.13@gmail.com Mobile number: 9123456789 Password: Kponce013! Confirm Password: Kponce013! Role: Barangay Request Manager Upload Photo: peakpx(2).jpg | M2-UC2.1-TC_06 | Should be able to create an account successfully and receive a success prompt | Account is successfully created with success prompt | PASS | function is working except for the routing in hosted site, must add image max size error handler or increase the max size of accepted photo | 2023-09-21
TC_08 | Admin creates an account with valid but incomplete required input | First name: Kieyl Ponce Middle name: No middle name checkbox: unchecked Surname: Gender: Male Marital Status: Single Nationality: Filipino Birthdate: December 13, 2001 Place of Birth: Taguig, NCR Address-Street: Quintar Address-Zone/Purok: Zone 1 Employee ID: 1234567 Email Address: kieyldecastroponce.13@gmail.com Mobile number: 91234567 Password: Kponce013! Confirm Password: Kponce013! Role: Barangay Request Manager | M2-UC2.1-TC_06 | System will prompt error signs to missing fields that are required, account creation will not proceed | System prompts error signs to required missing fields, account creation did not proceed | PASS |  | 2023-09-21
TC_09 | Admin creates an account with invalid but complete required input | First name: Kieyl Middle name: De Castro No middle name checkbox: unchecked Surname: Ponce Suffix: None Gender: Male Marital Status: Single Nationality: Filipino Birthdate: September 23, 2023 Place of Birth: Taguig, NCR Address-Block No.: Block 7 Address-Street: Quintar Address-Zone/Purok: Zone 1 Employee ID: 1234567 Email Address: kieyldecastroponce.13@gmail.com Mobile number: 9123456789 Password: Kponce013! Confirm Password: Kponce013! Role: Barangay Request Manager Upload Photo: peakpx(2).jpg | M2-UC2.1-TC_06 | System will prompt error signs to fields with invalid value, account creation will not proceed | There are system prompts fo most of fields if the value inputted is invalid except the birthdate. The birthdate input accepted the date that has not yet arrived. [Test Data for Birthdate: September 23, 2023] and the account creation succeeded. | FAIL |  | 2023-09-21
TC_10 | Admin creates an account button with no input | No input | M2-UC2.1-TC_06 | System will prompt error signs to missing fields that are required, account creation will not proceed | System prompt error signs to missing fields that are required, account creation did not proceed | PASS |  | 2023-09-21
UC2-2 Admin - Deactivate Employee Account
TC_11 | Verify if Admin can click "Deactivate" button in List of Barangay Employee Account | No input required | M2-UC2.1-TC_05 | Should be prompted with password input for deactivating an account | Prompted with password input for deactivating an account | PASS
TC_12 | Admin deactivates an account and inputs correct password on the deactivation prompt | Password: Admin1_123 | M2-UC2.2-TC_11 | Should be able to deactivate the account | Selected account is deactivated with success message | PASS | function is working except for the routing in hosted site | 2023-09-21
TC_13 | Admin deactivates an account and inputs incorrect password on the deactivation prompt | Password: Admin1 | M2-UC2.2-TC_11 | Should be prompted with inavlid password error message | Should be prompted with invalid password error message | PASS |  | 2023-09-21
TC_14 | Admin clicks "Cancel" button | No input Required | M2-UC2.2-TC_11 | Should go back to the List of Barangay Employee Account | Goes back to the List of Barangay Employee Account | PASS |  | 2023-09-21
UC2.3 Admin - Reactivate Employee Account
TC_15 | Verify if the Admin can access Deactivated Employee Account from Manage Employee Account dropdown | No input required | M2-UC2.1-TC_05 | Should be redirected to the list of Deactivated Employee account page | Redirected to the list of Deactivated Employee account page | PASS | function is working except for the routing in hosted site | 2023-09-21
TC_16 | Admin reactivates an account and inputs correct password on the reactivation prompt | Password: Admin1_123 | M2-UC2.3-TC_15 | Should be able to succesfully recover the account | Did not succesfully recover the account | FAIL |  | 2023-09-21
TC_17 | Admin reactivates an account and inputs incorrect password on the reactivation prompt | Password: Admin1 | M2-UC2.3-TC_15 | Should be prompted with invalid password, reactivation will not be successful | Prompted with invalid password, reactivation is not successful | PASS |  | 2023-09-21
TC_18 | Admin clicks "Cancel" button | No Input Required | M2-UC2.3-TC_15 | Should be able to cancel account reactivation and will go back to the list of Deactivated Employee account | Cancelled account reactivation and goes back to the list of Deactivated Employee account | PASS |  | 2023-09-21
UC2.4 Admin - Edit Employee Account
TC_19 | Verify if the Admin can access List of Barangay Employee Account from the Manage Employee Account dropdown | No input required | M2-UC2.1-TC_05 | Should redirect to the List of Barangay Employee Account page | Redirected to the List of Barangay Employee Account page | PASS |  | 2023-09-21
TC_20 | Verify if the list of Active Employee from the table can be exported as PDF/Excel | No input required | M2-UC2.4-TC_19 | Should have a downloaded copy of the barangay employee list in excel/pdf format | Downloaded copies of the barangay employee list in excel/pdf format | PASS |  | 2023-09-21
TC_21 | Verify if the Admin can click "View" from the list of barangay employee account | No input required | M2-UC2.4-TC_19 | Should redirect to the Employee Account Information | Redirected to the Employee Account Information | PASS |  | 2023-09-21
TC_22 | Verify if the Admin can click "Edit" button | No input required | M2-UC2.4-TC_21 | Should be able to see a fillable employee account information form | Allowed to fill employee account information form | PASS |  | 2023-09-21
TC_23 | Admin updates an account with valid and complete required input | First name: Kieyl Middle name: De Castro No middle name checkbox: unchecked Surname: Ponce Suffix: None Gender: Male Marital Status: Married Nationality: Filipino Birthdate: December 13, 2001 Place of Birth: Taguig, NCR Address-Block No.: Block 9 Address-Street: Quintar Address-Zone/Purok: Zone 12 Employee ID: 1234567 Email Address: kieyldecastroponce.13@gmail.com Mobile number: 9123456789 Password: Kponce013! Confirm Password: Kponce013! Role: Barangay Request Manager Upload Photo: peakpx(2).jpg | M2-UC2.4-TC_22 | Should be succesful in updating the account information with success prompt | Succesful update of the account information with success prompt | PASS |  | 2023-09-21
TC_24 | Admin updates an account with valid but incomplete required input | First name: Kieyl Middle name: De Castro No middle name checkbox: unchecked Surname: Ponce Suffix: None Gender: Male Marital Status: Married Nationality: Filipino Birthdate: December 13, 2001 Place of Birth: Taguig, NCR Address-Block No.: Block 9 Address-Street: Quintar Address-Zone/Purok: Zone 12 Employee ID: 1234567 Email Address: kieyldecastroponce.13@gmail.com Mobile number: --- Password: Kponce013! Confirm Password: Kponce013! Role: Barangay Request Manager Upload Photo: peakpx(2).jpg | M2-UC2.4-TC_22 | System will prompt error signs to missing fields that are required, updating will not proceed | System prompted error signs to missing fields that are required, updating did not proceed | PASS |  | 2023-09-21
TC_25 | Admin updates an account with invalid but complete required input | First name: Kieyl Middle name: De Castro No middle name checkbox: unchecked Surname: Ponce Suffix: None Gender: Male Marital Status: Married Nationality: Filipino Birthdate: September 23, 2023 Place of Birth: Taguig, NCR Address-Block No.: Block 9 Address-Street: Quintar Address-Zone/Purok: Zone 12 Employee ID: 1234567 Email Address: kieyldecastroponce.13@gmail.com Mobile number: 91234 Password: Kponce013! Confirm Password: Kponce013! Role: Barangay Request Manager Upload Photo: peakpx(2).jpg | M2-UC2.4-TC_22 | System will prompt error signs to invalid fields that are required, updating will not proceed | There are system prompts fo most of fields if the value inputted is invalid except the birthdate. The birthdate input accepted the date that has not yet arrived. [Test Data for Birthdate: September 23, 2023] and the account update succeeded. | FAIL |  | 2023-09-21
TC_26 | Admin updates an account with no input | No input | M2-UC2.4-TC_22 | System will prompt error signs to invalid fields that are required, updating will not proceed | Prompt error signs to invalid fields that are required, updating did not proceed | PASS |  | 2023-09-21
TC_27 | Verify if the Admin can click "Reset Password" button | No input required | M2-UC2.4-TC_22 | Should see a prompt with new password and confirm password input | Prompted with new password and confirm password input | PASS |  | 2023-09-21
TC_28 | Admin updates the password with valid new password and same input in confirm password | New Password: KPonce01! Confirm Password: KPonce01! | M2-UC2.4-TC_27 | Password should be updated with success message | Password was updated with success message | PASS |  | 2023-09-21
TC_29 | Admin updates the password with valid new password and different password in confirm password input | New Password: KPonce01! Confirm Password: KPonce01!! | M2-UC2.4-TC_27 | Cconfirm password input should have an error message that says passwords do not match | Cconfirm password input had an error message that says passwords do not match | PASS |  | 2023-09-21
TC_30 | Admin updates the password using an old password | New Password: KPonce013! Confirm Password: KPonce013!! | M2-UC2.4-TC_27 | Should see a prompt that the password used was an old password | Prompted with message the password used was an old password | PASS |  | 2023-09-21
UC2.5 Employee - Edit Employee Account
TC_31 | Verify if the Barangay Employee can click "Account Setting" from clicking the profile | No input required | M1-UC1.1-TC_02 | Should redirect to the "My Account" page | Redirected to the "My Account" page | PASS | function is working except for the routing in hosted site | 2023-09-21
TC_32 | Verify if the Barangay Employee can click "Change Password" button | No input required | M2-UC2.5-TC_31 | Should see a prompt of Change Password form | Prompted with Change Password form | PASS |  | 2023-09-21
TC_33 | Barangay Employee updates the password with inputs old password, new password and same password in confirm password | Old Password: Admin1_123 New Password: Admin_11 Confirm New Password: Admin_11 | M2-UC2.5-TC_32 | Password should be updated with success message | Password was updated with success message | PASS |  | 2023-09-21
TC_34 | Barangay Employee updates the password with invalid old password or new password or different password in confirm new password | Old Password: Admin1_ New Password: Admin_11 Confirm New Password: Admin_111 | M2-UC2.5-TC_32 | Should see a prompt for error message in the input fields | Prompted with error message in the input fields | PASS |  | 2023-09-21
TC_35 | Barangay Employee updates the password using an old password on the new password input | Old Password: Admin1_123 New Password: Admin1_123 Confirm New Password: Admin1_123 | M2-UC2.5-TC_32 | Should see a prompt that the password used was an old password | Prompted with that the password used was an old password | PASS |  | 2023-09-21
TC_36 | Barangay Employee clicks "Cancel" button | No input required | M2-UC2.5-TC_32 | Should close the Change Password Form | Change Password Form was closed | PASS |  | 2023-09-21
TC_37 | Verify if the Barangay Employee can click "Change Email" button | No input required | M2-UC2.5-TC_31 | Should see a prompt of Change Email form | Prompted with Change Email form | PASS |  | 2023-09-21
TC_38 | Barangay Employee updates the email using a new email | New Email: admin11@gmail.com | M2-UC2.5-TC_37 | Should successfully save the new email with success message | New email is saved with success message | PASS |  | 2023-09-21
TC_39 | Barangay Employee updates the email using an old email | New Email: admin@gmail.com | M2-UC2.5-TC_37 | Should receive a prompt that the email used is the old email | Prompted with message the email used is the old email | PASS |  | 2023-09-21
TC_40 | Barangay Employee updates the email with no input | No input | M2-UC2.5-TC_37 | Should see an error message under the input box to fill in the new email | An error message under the input box was shown | PASS |  | 2023-09-21
TC_41 | Barangay Employee clicks "Cancel" button | No input | M2-UC2.5-TC_37 | Should close the Change Email Form | Change Email Form was closed | PASS |  | 2023-09-21
TC_42 | Barangay Employee updates the mobile number with new mobile number | Mobile No.: +63987654321 | M2-UC2.5-TC_31 | Should succesfully save the new mobile number with success message | New mobile number is saved with success message | PASS |  | 2023-09-21
TC_43 | Barangay Employee updates the mobile number using an old mobile number | Mobile No.: +63987654321 | M2-UC2.5-TC_43 | Should receive a prompt that the number used is the old number | Prompted with messahe the number used is the old number | PASS |  | 2023-09-21
TC_44 | Barangay Employee updates the mobile number using no input | No input | M2-UC2.5-TC_43 | Should see an error message under the input box to fill in the new number | An error message under the input box was shown | PASS |  | 2023-09-21
TC_45 | Barangay Employee clicks "Cancel" button | No input required | M2-UC2.5-TC_43 | Should close the Change Mobile Number form | Change Mobile number form was closed | PASS |  | 2023-09-21
TC_46 | Barangay Employee clicks "Back" button | No input required | M2-UC2.5-TC_31 | Should return to the previous page | Returned to the previous page | PASS |  | 2023-09-21

## M3-Manage Resident Account
TEST CASE PLANNING AND EXECUTION
| TEST TITLE | PRIORITY | TEST CASE ID | TEST NUMBER | TEST DATE |  |  | PRIORITY KEY
| Manage Resident Account | HIGH | TC_47 - TC_55 | 6 | 2023-09-28 |  |  | LOW
| TEST DESCRIPTION |  | TEST DESIGNED BY | TEST EXECUTED BY | EXECUTION DATE |  |  | MEDIUM
| Test on Managing Resident Accounts |  | Ruth R. Morallos | Ruth R. Morallos | 2023-09-28 |  |  | HIGH
| TEST DESCRIPTION |  | TEST DEPENDENCIES | TEST CONDITIONS
| Test on Managing Resident Accounts |  | The database for the User should be working. | Administrator should be logged in but in the admin portal.
Test Case ID | STEPS | TEST DATA | PRE-REQUISITE | EXPECTED RESULTS | ACTUAL RESULTS[SPRINT 1] | PASS / FAIL | ADDITIONAL NOTES | TEST DATE
UC3.1 Deactivate Resident Account
TC_47 | Verify if the Admin can access Manage Resident Account | No input required | M1-UC1.1-TC_02 | Should be able to see a dropdown with List of Resident and Deactivated Resident Account option | A dropdown with List of Resident and Deactivated Resident Account option is shown | PASS |  | 2023-09-21
TC_48 | Verify if the Admin can access List of Resident Account from the dropdown | No input required | M3-UC3.1-TC_47 | Should redirect to Active Residents page | Redirected to Active Residents page | PASS | function is working except for the routing in hosted site | 2023-09-21
TC_49 | Verify if the Admin can filter the list of Barangay Employee Account using valid inputs | Gender: Male Street: All | M3-UC3.1-TC_48 | Should be able to see the Male Residents in all Streets in the table | A list of Male Residents in all Streets are shown in the table | PASS |  | 2023-09-21
TC_50 | Verify if the list of Residents from the table can be exported as PDF/Excel | No input required | M3-UC3.1-TC_48 | Should have a downloaded copy of the barangay residents list in excel/pdf format | Downloaded copies of the barangay residents list in excel/pdf format | PASS |  | 2023-09-21
TC_51 | Admin selects and deactivates an account and inputs correct password on the deactivation prompt | Password: Admin1_123 | M3-UC3.1-TC_48 | Selected account should be deactivated with success message | Selected account was not deactivated | FAIL |  | 2023-09-21
TC_52 | Admin selects and deactivates an account and inputs correct password on the deactivation prompt | Password: Admin1_1 | M3-UC3.1-TC_48 | Should receive a prompt that says the password is incorrect | Did not receive a prompt that says the password is incorrect | FAIL |  | 2023-09-21
UC3.2 Reactivtate Resident Account
TC_53 | Verify if the Admin can access Deactivated Resident Account from the dropdown | No input required | M3-UC3.1-TC_47 | Should be redirected to the list of Deactivated Employee account page | Redirected to the list of Deactivated Employee account page | PASS | function is working except for the routing in hosted site | 2023-09-22
TC_54 | Admin selects and reactivates an account and inputs correct password on the reactivation prompt | Password: Admin1_123 | M3-UC3.2-TC_53 | Should be able to succesfully reactivate the account with success message | Did not reactivate the account | FAIL |  | 2023-09-22
TC_55 | Admin selects and reactivates an account and inputs incorrect password on the reactivation prompt | Password: Admin1_1 | M3-UC3.2-TC_53 | Should receive a prompt that says the password is incorrect | Did not receive a prompt that says the password is incorrect | FAIL |  | 2023-09-22

## M4-Manage Web-App
TEST CASE PLANNING AND EXECUTION
| TEST TITLE | PRIORITY | TEST CASE ID | TEST NUMBER | TEST DATE | PRIORITY KEY
| Manage Web-App | HIGH | TC_56-TC_74 | 6 | 2023-09-28 | LOW
| TEST DESCRIPTION |  | TEST DESIGNED BY | TEST EXECUTED BY | EXECUTION DATE | MEDIUM
| Test on processing management of Web - App |  | Ruth R. Morallos | Ruth R. Morallos | 2023-09-28 | HIGH
| TEST DESCRIPTION |  | TEST DEPENDENCIES | TEST CONDITIONS
| Test on processing management of Web - App |  | The database for the User and Manage Web App should be available | Administrator should logged in but in the admin portal.
Test Case ID | STEPS | TEST DATA | PRE-REQUISITE | EXPECTED RESULTS | ACTUAL RESULTS[SPRINT 1] | PASS / FAIL | ADDITIONAL NOTES | TEST DATE
UC4.1 Edit Homepage Banner
TC_56 | Verify if the Admin can click "Manage Website" | No input required | M1-UC1.1-TC_02 | Should redirect to Manage Web Application Page | Redirected to Manage Web Application Page | PASS |  | 2023-09-19
TC_57 | Verify if the Admin can click "Edit banner" button | No input required | M4-UC4.1-TC_56 | Should proceed to edit banner prompt | Edit banner prompt is shown | PASS |  | 2023-09-19
TC_58 | Verify if the Admin can click "Update Banner #1/#2/#3/#4 | No input required | M4-UC4.1-TC_57 | Should show an additional input box for images | Additional input box for images is shown | PASS |  | 2023-09-19
TC_59 | Verify if the Admin can add images in "Choose Photo" input | No input required | M4-UC4.1-TC_58 | Should open the file explorer to chose photos from | File explorer was opened | PASS |  | 2023-09-19
TC_60 | Admin updates the banner with image input | banner.jpg | M4-UC4.1-TC_59 | The banner should be updated in the home page | The banner was updated in the home page | PASS |  | 2023-09-19
TC_61 | Admin updates the banner without image input | No input | M4-UC4.1-TC_59 | The banner should be the same as the old banner in the home page | The banner was the same as the old banner in the home page | PASS |  | 2023-09-19
TC_62 | Admin clicks "Close" button | No input required | M4-UC4.1-TC_59 | Should close the Edit Banner prompt | Edit Banner prompt was closed | PASS |  | 2023-09-19
UC4.2 Edit Demography
TC_63 | Verify if the Admin can click "Edit Demography" button | No input required | M4-UC4.1-TC_56 | Should proceed to edit demography prompt | Edit demography prompt is shown | PASS |  | 2023-09-19
TC_64 | Admin updates the demography with new information | Total Land Area: 802100 Population: 42997 Registered Voters: 22959 Household: 8507 No. of Puroks: 57 No. of Streets: 64 No. of Polling Preints: 104 | M4-UC4.2-TC_63 | The demography should be updated with the new information in the home page and success message | The demography was updated with the new information in the home page and success message | PASS |  | 2023-09-19
TC_65 | Admin updates the demography with old information | Total Land Area: 802147 Population: 42997 Registered Voters: 22959 Household: 8507 No. of Puroks: 57 No. of Streets: 64 No. of Polling Precincts: 104 | M4-UC4.2-TC_63 | The demography should have no changes and shows success message | The demography had no changes and shows success message | PASS |  | 2023-09-19
TC_66 | Admin clicks "Close" button | No input required | M4-UC4.2-TC_63 | Should close the Edit Demography prompt | Edit Demography prompt was closed | PASS |  | 2023-09-19
UC4.3 Edit Contacts
TC_67 | Verify if the Admin can click "Edit Contacts" button | No input required | M4-UC4.1-TC_56 | Should proceed to edit contact prompt | Edit contact prompt is shown | PASS |  | 2023-09-19
TC_68 | Admin updates the Barangay Contacts with new information | Telephone: 88660789 Smart: 09491551111 Sun: 09236152389 Globe: 09956531922 Fire Station: 88370740 Taguig Rescue: 86407006 Taguig Police: 86423582 Police Station 6: 09171843906 | M4-UC4.3-TC_67 | The contacts should be updated with the new information in the home page and success message | The contacts was updated with the new information in the home page and success message | PASS |  | 2023-09-19
TC_69 | Admin updates the Barangay Contacts with old information | Telephone: 88660385 Smart: 09491551111 Sun: 09236152389 Globe: 09956531922 Fire Station: 88370740 Taguig Rescue: 86407006 Taguig Police: 86423582 Police Station 6: 09171843906 | M4-UC4.3-TC_67 | The contacts should have no changes and shows success message | The contacts had no changes and shows success message | PASS |  | 2023-09-19
TC_70 | Admin clicks "Close" button | No input required | M4-UC4.3-TC_67 | Should close the Edit Contacts prompt | Edit Contacts prompt was closed | PASS |  | 2023-09-19
UC4.4 Edit Barangay Officials
TC_71 | Verify if the Admin can click "Update Barangay Officials" button | No input required | M4-UC4.1-TC_56 | Should proceed to Update Barangay Officials prompt | Update Barangay Officials prompt is shown | PASS |  | 2023-09-19
TC_72 | Admin updates the Barangay Officials with new information of complete and valid inputs | Barangay Captain Full Name: Hon. Michelle Ann M. Odevilas Upload Image: capt.jpg Comitee on ways and means: Full name: Hon Kieyl V. Ponce Upload Image: wm.jpg | M4-UC4.4-TC_71 | The barangay officials should be updated with the new information in the home page and success message | The barangay officials was updated with the new information in the home page and success message | PASS |  | 2023-09-19
TC_73 | Admin updates the Barangay Officials with new information of incomplete and/or invalid inputs | Barangay Captain Full Name: Hon. Michelle Ann M. Odevilas Upload Image: capt.jpg Comitee on ways and means: Full name: Hon Glenn V. Daiz Upload Image: wm.jpg | M4-UC4.4-TC_71 | The barangay officials should have no changes and shows success message | The barangay officials had no changes and shows success message | PASS |  | 2023-09-19
TC_74 | Admin updates the Barangay Officials with old information | No input required | M4-UC4.4-TC_71 | Should close theUpdate Barangay Officials prompt | Update Barangay Officials prompt was closed | PASS |  | 2023-09-19

## M5-Online Request
TEST CASE PLANNING AND EXECUTION
| TEST TITLE | PRIORITY | TEST CASE ID | TEST NUMBER | TEST DATE | PRIORITY KEY
| Online Request | HIGH | TC_76 - TC_98 | 6 | 2023-09-28 | LOW
| TEST DESCRIPTION |  | TEST DESIGNED BY | TEST EXECUTED BY | EXECUTION DATE | MEDIUM
| Test on accessing the services and managing the requests for the available services |  | Ruth R. Morallos | Ruth R. Morallos & Kieyl Ponce | 2023-09-21 | HIGH
| TEST DESCRIPTION |  | TEST DEPENDENCIES | TEST CONDITIONS
| Test on accessing the services and managing the requests for the available services |  | The database for the Request, Request_Type, and User should be working. | Barangay Secretary and Request Manager should logged in but in the admin portal.
Test Case ID | STEPS | TEST DATA | PRE-REQUISITE | EXPECTED RESULTS | ACTUAL RESULTS[SPRINT 1] | PASS / FAIL | ADDITIONAL NOTES | TEST DATE
UC5.1 Manage Services
TC_76 | Verify if the Barangay Secretary can access "Manage Services" | No input required | M1-UC1.1-TC_02 | Should be redirected to Manage Services Page | Redirected to Manage Services Page | PASS |  | 2023-09-21
TC_77 | Barangay Secretary can set a service as Active or Inactive | No input required | M5-UC5.1-TC_76 | Should be able to choose between "Active/Inactive" in the dropdown of Action Column | Can set between "Active/Inactive" in the dropdown of Action Column | PASS |  | 2023-09-21
TC_78 | Barangay Secreatry updates the service with new Actions | No input required | M5-UC5.1-TC_77 | Should receive a succesful update prompt | Received a succesful update prompt | PASS |  | 2023-09-21
TC_79 | Barangay Secretary updates the service with old Actions | No input required | M5-UC5.1-TC_77 | Should still receive a succesful update prompt | Still able to receive a succesful update prompt | PASS |  | 2023-09-21
UC5.2 View Document Request
TC_80 | Verify if the Barangay Secretary can access View Document Request | No input required | M1-UC1.1-TC_02 | Should be redirected to Document Request | Redirected to Document Request | PASS |  | 2023-09-21
TC_81 | Verify if the list of Document Request from the table can be exported as PDF/Excel | No input required | M5-UC5.2-TC_80 | Should have a downloaded copy of the document request list in excel/pdf format | Can download copy of the document request list in excel/pdf format | PASS |  | 2023-09-21
TC_82 | Verify if the Barangay Secretary can view a document request from the list | No input required | M5-UC5.2-TC_80 | Should be able to view the information submitted by the requestor | Can view the information submitted by the requestor | PASS |  | 2023-09-21
UC5.3 Process Document Request
TC_83 | Verify if the Barangay Secretary can access Process Document Request | No input required | M1-UC1.1-TC_02 | Should be redirected to Process Document Request | Redirected to Process Document Request Page | PASS |  | 2023-09-21
TC_84 | Verify if the Barangay Secretary can process a document from the list | No input required | M5-UC5.3-TC_83 | Should be able to view the information submitted by the requestor | Can view the information submitted by the requestor | PASS |  | 2023-09-21
TC_85 | Barangay Secretary clicks "Reassign" button | No input required | M5-UC5.3-TC_84 | Should be prompted with reassign confirmation | Prompted with reassign confirmation | PASS |  | 2023-09-21
TC_86 | Barangay Secretary confirms reassign request | No input required | M5-UC5.3-TC_85 | Should be able to reassign a request to the barangay employee who are logged in | Request is reassigned to the barangay employee who are logged in | PASS |  | 2023-09-21
TC_87 | Barangay Secretary cancels reassign request | No input required | M5-UC5.3-TC_85 | Should go back to the information page | Goes back to the information page | PASS |  | 2023-09-21
UC5.4 Approve Document Request
TC_88 | Barangay Secretary clicks "Process" | No input required | M5-UC5.3-TC_84 | Should be able to see the information within the document and toggle between two options: "Accept request" or "Deny request" | Can see the information within the document and toggle between two options: "Accept request" or "Deny request" | PASS |  | 2023-09-21
TC_89 | Barangay Secretary selects "Accept" | No input required | M5-UC5.4-TC_88 | Should be able to see the "Accept request form" with "Date" and "Note" fields | Can see the "Accept request form" with "Date" and "Note" fields | PASS |  | 2023-09-21
TC_90 | Barangay Secretary accepts a request with valid date input and note | Date: 09/24/2023 - 09/25/2023 Note: "This is a valid note" | M5-UC5.4-TC_89 | Should display check marks within the filled in fields and be prompted for the secretary's password | Displays check marks within the filled in fields and be prompted for the secretary's password | PASS |  | 2023-09-21
TC_91 | Barangay Secretary accepts a request with valid date input and invalid note | Date: 09/24/2023 - 09/25/2023 Note: <no input> | M5-UC5.4-TC_89 | Should not be able to see the password prompt while displaying an exclamation mark on the missing fields | Cannot see the password prompt while displaying an exclamation mark on the missing fields | PASS |  | 2023-09-21
TC_92 | Barangay Secretary inputs correct password after accepting a request | Password: Secretary_123 | M5-UC5.4-TC_90 | Should proceed to accept document request and be prompted with a success message | Proceeds to accept the document request and be prompted with a success message | PASS |  | 2023-09-21
TC_93 | Barangay Secretary inputs incorrect password after accepting a request | Password: Secretary1234 | M5-UC5.4-TC_90 | Should not be able to make any changes within the document's status and be prompted with an error message | Cannot make any changes within the document's status and be prompted with an error message | PASS |  | 2023-09-21
UC5.5 Deny Document Request
TC_94 | Barangay Secretary selects "Deny" | No input required | M5-UC5.4-TC_88 | Should be able to see "Deny request" form asking for "reason/s to deny" | Can see "Deny request" form asking for "reason/s to deny" | PASS |  | 2023-09-21
TC_95 | Barangay Secretary denies a request with valid note | Note: "This is a valid note" | M5-UC5.5-TC_94 | Should display a check mark within the filled in field and be prompted for the secretary's password | Displays a check mark within the filled in field and be prompted for the secretary's password | PASS |  | 2023-09-21
TC_96 | Barangay Secretary denies a request with invalid note | Note: <no input> | M5-UC5.5-TC_94 | Should be able to see an exclamation mark on the missing field | Cannot see the password prompt while displaying an exclamation mark on the missing field | PASS |  | 2023-09-21
TC_97 | Barangay Secretary inputs correct password after denying a request | Password: Secretary_123 | M5-UC5.5-TC_95 | Should proceed to deny document request and be prompted with a success message | Proceeds to deny document request and be prompted with a success message | PASS |  | 2023-09-21
TC_98 | Barangay Secretary inputs incorrect password after denying a request | Password: Secretary1234 | M5-UC5.5-TC_95 | Should not be able to make any changes within the document's status and be prompted with an error message | Cannot able to make any changes within the document's status and be prompted with an error message | PASS |  | 2023-09-21

## M6-Online Concern
TEST CASE PLANNING AND EXECUTION
| TEST TITLE | PRIORITY | TEST CASE ID | TEST NUMBER | TEST DATE | PRIORITY KEY
| Online Request | HIGH | TC_99 - TC_125 | 6 | 2023-09-28 | LOW
| TEST DESCRIPTION |  | TEST DESIGNED BY | TEST EXECUTED BY | EXECUTION DATE | MEDIUM
| Test on processing the concerns |  | Ruth R. Morallos | Kieyl Ponce | 2023-09-24 | HIGH
| TEST DESCRIPTION |  | TEST DEPENDENCIES | TEST CONDITIONS
| Test on processing the concerns |  | The database for the Concern and User should be working. | Barangay Secretary and/or Concern Manager should BE logged but in the admin portal.
Test Case ID | STEPS | TEST DATA | PRE-REQUISITE | EXPECTED RESULTS | ACTUAL RESULTS[SPRINT 1] | PASS / FAIL | ADDITIONAL NOTES | TEST DATE
UC6.1 View Concern
TC_99 | Verify if the Barangay Secretary can access View Concern | No input required | M1-UC1.1-TC_02 | Should be redirected to "View Concern" page | Redirected to "View Concern" page | PASS |  | 2023-09-19
TC_100 | Verify if the Submitted Concerns from the table can be exported as PDF/Excel | No input required | M6-UC6.1-TC_99 | Should be able to download a PDF/Excel file of the submitter concerns table | Can download a PDF/Excel file of the submitter concerns table | PASS |  | 2023-09-19
TC_101 | Verify if the Barangay Secretary can access a submitted concern from the list | No input required | M6-UC6.1-TC_99 | Should be redirected to a page with the submitted concern | Redirected to a page with the submitted concern | PASS |  | 2023-09-19
TC_102 | Barangay Secretary clicks "Done" button | No input required | M6-UC6.1-TC_101 | Should go back to the "Submitted Concerns" list | Should go back to the "Submitted Concerns" list | PASS |  | 2023-09-19
UC6.2 Process Concern
TC_103 | Verify if the Barangay Secretary can access Process Concern | No input required | M1-UC1.1-TC_02 | Should be redirected to Process Concern Request | Redirected to Process Concern Request Page | PASS |  | 2023-09-19
TC_104 | Verify if the Barangay Secretary can process a concern from the list | No input required | M6-UC6.2-TC_103 | Should be able to view the information submitted by the sender | Can view the information submitted by the sender | PASS |  | 2023-09-19
TC_105 | Barangay Secretary clicks "Reassign" button | No input required | M6-UC6.2-TC_104 | Should be prompted with reassign confirmation | Prompted with reassign confirmation | PASS |  | 2023-09-19
TC_106 | Barangay Secretary confirms reassigning concern | No input required | M6-UC6.2-TC_105 | Should be able to reassign a concern to the barangay employee who are logged in | Concern is reassigned to the barangay employee who are logged in | PASS |  | 2023-09-19
TC_107 | Barangay Secretary cancels reassigning concern | No input required | M6-UC6.2-TC_105 | Should go back to the information page | Goes back to the information page | PASS |  | 2023-09-19
UC6.3 Update Concern
TC_108 | Verify if the Barangay Secretary can click "Update Request" | No input required | M6-UC6.2-TC_103 | Should prompt an "Update Concern" form requiring inputs for the Title and Details area | Displayed a prompt of an "Update Concern" form requiring inputs for the Title and Details area | PASS |  | 2023-09-19
TC_109 | Barangay Secretary updates a concern with complete and valid input | Title: Valid Title Details: Valid Details | M6-UC6.3-TC_108 | Should display check marks within the filled in fields and be prompted for the secretary's password | Displays check marks within the filled in fields and be prompted for the secretary's password | PASS |  | 2023-09-19
TC_110 | Barangay Secretary updates a concern with incomplete and/or invalid input | Title: Valid Title Details: <no input> | M6-UC6.3-TC_108 | Should not be able to see the password prompt while displaying an exclamation mark on the missing fields | Cannot see the password prompt while displaying an exclamation mark on the missing fields | PASS |  | 2023-09-19
TC_111 | Barangay Secretary updates a concern with no input | Title: <no input> Details: <no input> | M6-UC6.3-TC_108 | Should not be able to see the password prompt while displaying an exclamation mark on the missing fields | Cannot see the password prompt while displaying an exclamation mark on the missing fields | PASS |  | 2023-09-19
TC_112 | Barangay Secretary inputs correct password in the prompt after updating the concern | Password: Secretary_123 | M6-UC6.3-TC_109 | Should proceed to update concern and be prompted with a success message | Proceeds to update the concern and be prompted with a success message | PASS |  | 2023-09-19
TC_113 | Barangay Secretary inputs incorrect password in the prompt after updating the concern | Password: Secretary1234 | M6-UC6.3-TC_109 | Should not be able to make any changes within the concern and be prompted with an error message | Cannot make any changes within the concern and be prompted with an error message | PASS |  | 2023-09-19
UC6.4 Deny Concern
TC_114 | Verify if the Barangay Secretary can click "Deny Request" | No input required | M6-UC6.2-TC_103 | Should prompt a "Deny Request" form requiring inputs for the Title and Details area | Prompted a "Deny Request" form requiring inputs for the Title and Details area | PASS |  | 2023-09-19
TC_115 | Barangay Secretary denies a concern with complete and valid note input | Title: Valid Title Details: Valid Details | M6-UC6.4-TC_114 | Should display check marks within the filled in fields and be prompted for the secretary's password | Displays check marks within the filled in fields and be prompted for the secretary's password | PASS |  | 2023-09-19
TC_116 | Barangay Secretary denies a concern with incomplete and/or invalid note input | Title: Valid Title Details: <no input> | M6-UC6.4-TC_114 | Should not be able to see the password prompt while displaying an exclamation mark on the missing fields | Cannot see the password prompt while displaying an exclamation mark on the missing fields | PASS |  | 2023-09-19
TC_117 | Barangay Secretary denies a concern with no note input | Title: <no input> Details: <no input> | M6-UC6.4-TC_114 | Should not be able to see the password prompt while displaying an exclamation mark on the missing fields | Cannot see the password prompt while displaying an exclamation mark on the missing fields | PASS |  | 2023-09-19
TC_118 | Barangay Secretary inputs correct password in the prompt after denying the request | Password: Secretary_123 | M6-UC6.4-TC_115 | Should proceed to deny request and be prompted with a success message | Proceeds to deny the request and be prompted with a success message | PASS |  | 2023-09-19
TC_119 | Barangay Secretary inputs incorrect password in the prompt after denying the request | Password: Secretary1234 | M6-UC6.4-TC_115 | Should not be able to make any changes within the concern and be prompted with an error message | Cannot make any changes within the concern and be prompted with an error message | PASS |  | 2023-09-19
UC6.5 Close Concern
TC_120 | Verify if the Barangay Secretary can click "Close Concern" | No input required | M6-UC6.2-TC_103 | Should prompt an "Close Concern" form requiring inputs for the Title and Details area | Displayed a prompt of an "Close Concern" form requiring inputs for the Title and Details area | PASS |  | 2023-09-19
TC_121 | Barangay Secretary closes a concern with complete and valid note input | Title: Valid Title Details: Valid Details | M6-UC6.5-TC_120 | Should display check marks within the filled in fields and be prompted for the secretary's password | Displays check marks within the filled in fields and be prompted for the secretary's password | PASS |  | 2023-09-19
TC_122 | Barangay Secretary closes a concern with incomplete and/or invalid note input | Title: Valid Title Details: <no input> | M6-UC6.5-TC_120 | Should not be able to see the password prompt while displaying an exclamation mark on the missing fields | Cannot see the password prompt while displaying an exclamation mark on the missing fields | PASS |  | 2023-09-19
TC_123 | Barangay Secretary closes a concern with no note input | Title: <no input> Details: <no input> | M6-UC6.5-TC_120 | Should not be able to see the password prompt while displaying an exclamation mark on the missing fields | Cannot see the password prompt while displaying an exclamation mark on the missing fields | PASS |  | 2023-09-19
TC_124 | Barangay Secretary inputs correct password in the prompt after closing the concern | Password: Secretary_123 | M6-UC6.5-TC_121 | Should proceed to close the concern and be prompted with a success message | Proceeds to close the concern and be prompted with a success message | PASS |  | 2023-09-19
TC_125 | Barangay Secretary inputs incorrect password in the prompt after closing the concern | Password: Secretary1234 | M6-UC6.5-TC_121 | Should not be able to make any changes within the concern and be prompted with an error message | Cannot make any changes within the concern and be prompted with an error message | PASS |  | 2023-09-19

## M7-Generating Report
TEST CASE PLANNING AND EXECUTION
| TEST TITLE | PRIORITY |  | TEST CASE ID | TEST NUMBER | TEST DATE |  |  | PRIORITY KEY
| Online Request | HIGH |  | TC_126-TC_132 | 6 | 2023-09-28 |  |  | LOW
| TEST DESCRIPTION |  |  | TEST DESIGNED BY | TEST EXECUTED BY | EXECUTION DATE |  |  | MEDIUM
| Test on generating barangay reports |  |  | Ruth R. Morallos | Kieyl Ponce | 2023-09-24 |  |  | HIGH
| TEST DESCRIPTION |  |  | TEST DEPENDENCIES | TEST CONDITIONS
| Test on generating barangay reports |  |  | The database for the Request, Concern, and User should be working. | Barangay Captain should be logged in but in the admin portal.
Test Case ID | STEPS | TEST DATA | PRE-REQUISITE | EXPECTED RESULTS | ACTUAL RESULTS[SPRINT 1] | PASS / FAIL | ADDITIONAL NOTES | TEST DATE
UC7.1 Barangay Data Report
TC_126 | Verify if the Barangay Captain can click the dropdown of Reports | No input required | M1-UC1.1-TC_02 | Should be able to toggle through the following options within the dropdown: "Services," "Resident" and "Employee" | Can toggle through the following options within the dropdown: "Services," "Resident" and "Employee" | PASS |  | 2023-09-24
TC_127 | Barangay Captain clicks "Services" from the dropdown of Reports | No input required | M7-UC7.1-TC_126 | Should be redirected to the "Services Report" page of the dashboard. | It gives a 404 error and just goes back to the actual dashboard repetitively. | FAIL | the page for the actual service report is not accessible due to the error in the hosting path of the system. | 2023-09-24
TC_128 | Barangay Captain clicks "Show Request Statistics" from the Request Document Report panel | No input required | M7-UC7.1-TC_127 | Should expand to show the statistics regarding the number of requests received daily, weekly, monthly and/or yearly. | Dashboard expanded to show the statistics regarding the number of requests. | PASS |  | 2023-09-24
TC_129 | Barangay Captain clicks "Show Concern Statistics" from the Submitted Concern Report panel | No input required | M7-UC7.1-TC_127 | Should expand to show the statistics regarding the number of concerns received daily, weekly, monthly and/or yearly. | Dashboard expanded to show the statistics regarding the number of concerns received daily, weekly, monthly and/or yearly. | PASS |  | 2023-09-24
TC_130 | Barangay Captain clicks "Resident" from the dropdown of Reports | No input required | M7-UC7.1-TC_126 | Should be redirected to the "Resident Report" page of the dashboard. | Should be redirected to the "Resident Report" page of the dashboard. | PASS |  | 2023-09-24
TC_131 | Barangay Captain clicks "Employee" from the dropdown of Reports | No input required | M7-UC7.1-TC_126 | Should be redirected to the "Employee Report" page of the dashboard. | Should be redirected to the "Employee Report" page of the dashboard. | PASS |  | 2023-09-24
TC_132 | Barangay Captain can see all employees using the tab of Barangay Employee List | No input required | M7-UC7.1-TC_131 | Should be able to see the list of employees along with their roles, names, emails and IDs | Should be able to see the list of employees along with their roles, names, emails and IDs | PASS |  | 2023-09-24

## Available Test Data
AVAILABLE TEST DATA | DATABASE TABLE NAMES:
Administrator email: admin@gmail.com | concern
Password: Admin1_123 | concern history
manage_web_app
Secretary email: secretary@gmail.com | request_history
password: Secretary_123 | request_type
reset_password
Captain email: captain@gmail.com | users
Password: Captain_123 | visitor
Request Manager Email: request@gmail.com
Password: Request_123
Request Concern Email: concern@gmail.com
Password: Concern_123
TEST - QA
First name: Kieyl Middle name: De Castro No middle name checkbox: unchecked Surname: Ponce Suffix: None Gender: Male Marital Status: Single Nationality: Filipino Birthdate: December 13, 2001 Place of Birth: Taguig, NCR Address-Block No.: Block 7 Address-Street: Quintar Address-Zone/Purok: Zone 1 Employee ID: 1234567 Email Address: kieyldecastroponce.13@gmail.com Mobile number: 9123456789 Password: Kponce013! Confirm Password: Kponce013! Role: Barangay Request Manager Upload Photo: peakpx(2).jpg